DIGITALCLASSROOM PLAN

School/Center Name: Polk State Chain of Lakes Collegiate High School

Director Name: Bridget Fetter		E-Mail Address: bfetter@polk.edu

Phone Number: 863-298-6800

The intent of the School/Center Digital Classroom Plan (DCP) is to provide a perspective on what the School/Center considers being vital and critically important in relation digital learning implementation, the improvement of student performance outcomes, and how this progress will be measured.  The plan shall meet the unique needs of students, schools and personnel in the School/Center as required by s.1011.62 (12) (b), F.S.

Part I. 	DIGITAL CLASSROOMS PLAN - OVERVIEW

The School/Center’s overview component of the plan should document the School/Center's overall focus and direction with respect to how the incorporation and integration of technology into the educational program will improve student performance outcomes.

The general introduction/background/School or Center technology policies component of the plan should include, but not be limited to:

1.1 	School/Center Mission and Vision statements –

- Our vision: To excel in providing focused students a challenging environment where they can earn a high school diploma and college credits.

1.2 	School/Center Profile - Provide relevant social, economic, geographic and demographic factors influencing the School/Center’s implementation of technology.

- Profile available on our website: http://www.polk.edu/col

- A hard copy also enclosed.

1.3 	School/Center Team Profile - Provide the following contact information for each member of the School/Center team participating in the DCP planning process.   The individuals that participated should include but not be limited to:

  - the digital learning components should be completed with collaboration between School/Center instructional, curriculum and information technology staff as required in s.1011.62(12)(b), F.S.

  - development of partnerships with community, business and industry; and

  - integration of technology in all areas of the curriculum, ESOL and special needs including students with disabilities.

| Title/Role | Name: | Email/Phone: |
| --- | --- | --- |
| Information Technology School/Center Contact | Johnny Stewart | jstewart@polk.edu |
| Curriculum School/Center Contact | Richard Jeffries | rjeffries@polk.edu |
| Instructional School/Center Contact | Laura Abercrombie Lynsay McCaulley Misty Sparling | labercrombie@polk.edu lmccaulley@polk.edu msparling@polk.edu |
| Finance School/Center Contact | Erin Montgomery | emontgomery@polk.edu |
| School/Center Leadership Contact | Bridget Fetter | bfetter@polk.edu |

1.4 	Planning Process- Summarize the process used to write this plan including but not limited to:

  - how parents, school staff and others were involved;

  - development of partnerships with community, business and industry; and

  - integration of technology in all areas of the curriculum, ESOL and special needs including students with disabilities.

Our School Advisory Committee (SAC) meets three times a year, and we discuss academic usage of technology at those meetings. We obtain feedback from our parents and SAC members to ensure that we are doing our utmost on behalf of our students.

We took a group of faculty and staff to ISTE in Atlanta and the IBIS Best Practices conference during the summer of 2014. After those two conferences, a team of faculty and staff came together to discuss our technology implementation plan for the 2014-2015 school year. We took a needs assessment from our faculty for the projected technology needs to make sure that our faculty have the tools needed to achieve their achievement goals in the future.

Two of our faculty members participate in Polk State College’s technology cohort, Innov8 Academy, which focuses on research-based practices with academic implementation of technology for increased student performance. Innov8 members use an action research plan to hypothesize outcomes for technology usage and innovation and report their findings at the annual Professional Development Day in May, which Polk State sponsors.

We partner with Polk State College’s IT department to install and maintain our technology hardware. The IT department troubleshoots any problems, upgrades any software, and maintains our systems for optimal performance.  We collaborate with Polk’s Audio Visual department, as well, for innovative ideas for classroom enhancements.

1.5 	Multi-Tiered System of Supports (MTSS)- Summarize the process used to write this plan including but not limited to:

  - data-based problem-solving process used for the goals and need analysis established in the plan;

  - the systems in place to monitor progress of the implementation plans; and

  - the plan to support the implementation and capacity.

We administered a needs assessment for our faculty in the spring to prepare for the coming fall term. We also discuss technology throughout the school year, should anything innovative and new come to our attention.

We have professional development during the summer to learn about best practices with technology, new software and implementation ideas, and new ways to use current technology that we already possess.

We met in July 2014 to build a plan for our technology needs and usage, and we finalized this plan in September 2014.

Part II. DIGITAL CLASSROOMS PLAN –STRATEGY

STEP 1 – Need Analysis:

School/Centers should identify current School/Center needs based on student performance outcomes and other key measurable data elements for digital learning.

- Student Performance Outcomes

- Digital Learning and Technology Infrastructure

- Professional Development

- Digital Tools

- Online Assessments

- Highest Student Achievement

Student Performance Outcomes:

School/Centers shall improve classroom teaching and learning to enable all students to be digital learners with access to digital tools and resources for the full integration of the Florida Standards.

After completing the suggested activities for determining the student performance outcomes described in the DCP guidance document, complete the table below with the targeted goals for each school grade component.  School/Centers may add additional student performance outcomes as appropriate.  Examples of additional measures are District Improvement and Assistance Plan (DIAP) goals, district Annual Measurable Objectives (AMOs) and/or other goals established in the district strategic plan.

Data is required for the metrics listed in the table.  For the student performance outcomes, these data points can and should be pulled from the school and district school grades published at http://schoolgrades.fldoe.org.  School/Centers may choose to add any additional metrics that may be appropriate below in the table for School/Center provided outcomes.

| Student Performance Outcomes (Required) |  | Baseline | Target | Date for Target to be Achieved (year) |
| --- | --- | --- | --- | --- |
|  | ELA Student Achievement | See attached. |  |  |
|  | Math Student Achievement | See attached. |  |  |
|  | Science Student Achievement | See attached. |  |  |
|  | ELA Learning Gains | See attached. |  |  |
|  | Math Learning Gains | See attached. |  |  |
|  | ELA Learning Gains of the Low 25% | N/A* |  |  |
|  | Math Learning Gains of the Low 25% | N/A* |  |  |
|  | Overall, 4-year Graduation Rate | 99.75% | 99.76% | 2015 |
|  | Acceleration Success Rate | N/A* |  |  |
| Student Performance Outcomes (School/Center Provided) |  | Baseline | Target | Date for Target to be Achieved (year) |

* These categories do not apply due to the following factors: We do not give the assessments, and we are not a part of the differentiated accountability model.  We are grades 11 & 12 only.

- Quality Efficient Services

Technology Infrastructure:

School/Centers shall create a digital learning infrastructure with the appropriate levels of bandwidth, devices, hardware and software.

For the infrastructure needs analysis, the required data points can and should be pulled from the Technology Readiness Inventory (TRI) if the data is accurate.  School/Centers may choose to add any additional metrics that may be appropriate.

| Infrastructure Needs Analysis (Required) |  | Baseline | Target | Date for Target to be Achieved (year) |
| --- | --- | --- | --- | --- |
|  | Student to Computer Device Ratio | 291:189 |  |  |
|  | Count of student instructional desktop computers meeting specifications | 29 |  |  |
|  | Count of student instructional mobile computers (laptops) meeting specifications | 89 | 139 | June 2016 |
|  | Count of student web-thin client computers meeting specifications | N/A |  |  |
|  | Count of student large screen tablets meeting specifications | 58 |  |  |
|  | Percent of schools meeting recommended bandwidth standard | 1GB | 1GB | Already met. |
|  | Percent of wireless classrooms (802.11n or higher) | 33% | 100% | June 2017 |
| Infrastructure Needs Analysis (School/Center Provided) |  | Baseline | Target | Date for Target to be Achieved (year) |

- Skilled Workforce and Economic Development

Professional Development:

Instructional personnel and staff shall have access to opportunities and training to assist with the integration of technology into classroom teaching.

Professional Development should be evaluated based on the level of current technology integration by teachers into classrooms.   This will measure the impact of the professional development for digital learning into the classrooms.   The Technology Integration Matrix (TIM) can be found at: http://fcit.usf.edu/matrix/matrix.php.  Average integration should be recorded as the percent of teachers at each of the 5 categories of the TIM for the levels of technology integration into the classroom curriculum:

- Entry

- Adoption

- Adaptation

- Infusion

- Transformation

| Professional Development Needs Analysis (Required) |  | Baseline | Target | Date for Target to be Achieved (year) |
| --- | --- | --- | --- | --- |
|  | Average Teacher technology integration via the TIM | 100% | 100% | Already met. |
|  | Average Teacher technology integration via the TIM (Elementary Schools) | N/A |  |  |
|  | Average Teacher technology integration via the TIM (Middle Schools) | N/A |  |  |
|  | Average Teacher technology integration via the TIM (High Schools) | 100% | 100% | Already met. |
|  | Average Teacher technology integration via the TIM (Combination Schools) | N/A |  |  |
| Professional Development Needs Analysis (School/Center Provided) |  | Baseline | Target | Date for Target to be Achieved (year) |

- Seamless Articulation and Maximum Access

Digital Tools:

School/Centers shall continue to implement and support a digital tools system that assists School/Center instructional personnel and staff in the management, assessment and monitoring of student learning and performance.

A key component to digital tools is the implementation and integration of a digital tool system that assists School/Center instructional personnel and staff in the management, assessment and monitoring of student learning and performance.  School/Centers may also add metrics for the measurement of CAPE digital tools.  For the required metrics of the digital tool system need analysis, please use the following responses:

| Baseline Response: | Target Response: |
| --- | --- |
| Fully implemented | Will continue to support and employ in classrooms |
| Partially implemented | Will work to implement and employ |
| Partially implemented | Maintain system |
| No system in place | Will work to implement and employ |
| No system in place | No plans to address at this time |

| Digital Tools Needs Analysis (Required) |  | Baseline | Target | Date for Target to be Achieved (year) |
| --- | --- | --- | --- | --- |
|  | Implementation status a system that enables teachers and administrators to access information about benchmarks and use it to create aligned curriculum guides. | Partially implemented | Will work to implement and employ | June 2016 |
|  | Implementation status of a system that provides teachers and administrators the ability to create instructional materials and/or resources and lesson plans. | Fully implemented | Will continue to support and employ in classrooms | Already met and will continue to meet. |
|  | Implementation status of a system that supports the assessment lifecycle from item creation, to assessment authoring and administration, and scoring. | No system in place. | No plans to address at this time. |  |
|  | Implementation status of a system that includes School/Center staff information combined with the ability to create and manage professional development offerings and plans. | Partially implemented | Maintain system | June 2015 |
|  | Implementation status of a system that includes comprehensive student information that is used to inform instructional decisions in the classroom, for analysis and for communicating to students and parents about classroom activities and progress. | No system in place | No plans to address at this time. |  |
|  | Implementation status of a system that leverages the availability of data about students, School/Center staff, benchmarks, courses, assessments and instructional resources to provide new ways of viewing and analyzing data. | Partially implemented | Maintain system. | June 2016 |
|  | Implementation status of a system that houses documents, videos, and information for teachers, students, parents, School/Center administrators and technical support to access when they have questions about how to use or support the system. | Fully implemented | Will continue to support and employ in classrooms | Already met |
|  | Implementation status of a system that includes or seamlessly shares information about students, School/Center staff, benchmarks, courses, assessments and instructional resources to enable teachers, students, parents, and School/Center administrators to use data to inform instruction and operational practices. | Partially implemented | Maintain system. | June 2016 |
|  | Implementation status of a system that provides secure, role-based access to its features and data for teachers, students, parents, School/Center administrators and technical support. | No system in place | No plans to address at this time. |  |
| Digital Tools Needs Analysis (School/Center Provided) |  | Baseline | Target | Date for Target to be Achieved (year) |

- Quality Efficient Services

Online Assessment Readiness:

School/Centers shall work to reduce the amount time used for the administration of computer-based assessments.

Online assessment (or computer-based testing) will be measured by the computer-based testing certification tool and the number of devices available and used for each assessment window.

| Online Assessments Needs Analysis (Required) |  | Baseline | Target | Date for Target to be Achieved (year) |
| --- | --- | --- | --- | --- |
|  | Computer-Based Assessment Certification Tool completion rate for schools in the School/Center (Spring 2014) | 25 | 25 | Already met. |
|  | Computers/devices required for assessments (based on schedule constraints) | 25 | 50 | March 2015 |
| Online Assessments Needs Analysis (School/Center Provided) |  | Baseline | Target | Date for Target to be Achieved (year) |

STEP 2 – Goal Setting:

Provide goals established by the School/Center that support the School/Centers mission and vision.  These goals may be the same as goals or guiding principles the School/Center has already established or adopted.

These should be long-term that focus on the needs of the School/Center identified in step one.  The goals should be focused on improving education for all students including those with disabilities.  These goals may be already established goals of the School/Center and strategies in step 3 will be identified for how digital learning can help achieve these goals.

Goals Examples:

EXAMPLES

- Highest Student Achievement: All schools will meet federal AMO benchmarks and meet expected growth on state assessments.

- Seamless Articulation and Maximum Access:  All students will have opportunities for industry certifications and are prepared to enter postsecondary with the skills necessary to succeed.

- Skilled Workforce and Economic Development: All teachers will have opportunities for professional development to develop skills for implementing digital learning into the curriculum.

- Quality Efficient Services: All school sites will be safe and effective environments to support developing students.

Enter School/Center goals below:

Our Vision: To excel in providing focused students a challenging environment where they can earn a high school diploma and college credits.

Our School/Center Goal:

- All school sites will be safe and effective environments to support developing students.

STEP 3 – Strategy Setting:

School/Centers will outline high-level digital learning and technology strategies that will help achieve the goals of the School/Center.  Each strategy will outline the School/Centers theory-of-action for how the goals in Step 2 will be addressed.  Each strategy should have a measurement and timeline estimation.

Examples of Strategies:

| EXAMPLES |  |  |  |
| --- | --- | --- | --- |
| Goal Addressed | Strategy | Measurement | Timeline |
| Highest student achievement | Supply teachers and students with high quality digital content aligned to the Florida Standards | - Purchase Instructional Materials in digital format | 50% of purchases in 2014-2015 |
| Highest student achievement | Continue support of an integrated digital tool system to aid teachers in providing the best education for each student. | - Fully implement system across nine components - Integrate instructional materials into system | 2014 and ongoing |
| Highest student achievement | Create an infrastructure that supports the needs of digital learning and online assessments | - Bandwidth amount - Wireless access for all classrooms | 2014-2019 |

Enter the School/Center strategies below:

| Goal Addressed | Strategy | Measurement | Timeline |
| --- | --- | --- | --- |
| Highest student achievement | Create an infrastructure that supports the needs of digital learning and online assessments | - Bandwidth amount Wireless access for all classrooms | June 2017 |

In addition, if the School/Center participates in federal technology initiatives and grant programs, please describe below a plan for meeting requirements of such initiatives and grant programs.

Part III. DIGITAL CLASSROOMS PLAN - ALLOCATION PROPOSAL

The DCP and the DCP Allocation must include five key components as required by s.1011.62(12)(b), F.S. In this section of the DCP, School/Centers will outline specific deliverables that will be implemented in the current year that are funded from the DCP Allocation.  The five components that are included are:

- Student Performance Outcomes

- Digital Learning and Technology Infrastructure

- Professional Development

- Digital Tools

- Online Assessments

This section of the DCP will document the activities and deliverables under each component.  The section for each component include, but are not limited to:

- Implementation Plan – Provide details on the planned deliverables and/or milestones for the implementation of each activity for the component area.  This should be specific to the deliverables that will be funded from the DCP Allocation.

- Evaluation and Success Criteria – For each step of the implementation plan, describe process for evaluating the status of the implementation and once complete, how successful implementation will be determined.  This should include how the deliverable will tie to the measurement of the student performance outcome goals established in component A.

A) Student Performance Outcomes

School/Centers will determine specific student performance outcomes based on School/Center needs and goals that will be directly impacted by the DCP Allocation.  These outcomes can be specific to an individual school site, grade level/band, subject or content area, or School wide.  These outcomes are the specific goals that the School/Center plans to improve through the implementation of the deliverables funded by the DCP Allocation for the 2014-15 school year.

| EXAMPLES |  |  |  |
| --- | --- | --- | --- |
| Student Performance Outcomes |  | Baseline | Target |
|  | Increase percent of fourth grade mathematics students performing at Sunshine Elementary school. | 45% | 48% |
|  | Improve graduation rates at Sandy Shores High school. | 78% | 80% |

Enter the School/Center student performance outcomes for 2014-15 that will be directly impacted by the DCP Allocation below:

| Student Performance Outcomes |  | Baseline | Target |
| --- | --- | --- | --- |
|  | Maintain high graduation rate | 99% | 99% |

B) Digital Learning and Technology Infrastructure

State recommendations for technology infrastructure can be found at http://www.fldoe.org/BII/Instruct_Tech/pdf/Device-BandwidthTechSpecs.pdf.  These specifications are recommendations that will accommodate the requirements of state supported applications and assessments.

Implementation Plan for B) Digital Learning and Technology Infrastructure:

| EXAMPLES |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Infrastructure Implementation |  |  |  |  |  |
|  | Deliverable | Estimated Completion Date | Estimated Cost | School/ School/Center | Outcome from Section A) |
| B.X. | Purchase and implement wireless access points | May 2015 | $4,000 | All fourth grade classes at Sunshine Elementary school. | Outcome Example 1 |
| B.X. | Purchase and implement 100 new student laptop devices | February 2015 | $6,000 | All fourth grade classes at Sunshine Elementary school. | Outcome Example 1 |

| Infrastructure Implementation |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Deliverable | Estimated Completion Date | Estimated Cost | School/ School/Center | Outcome from Section A) |
|  | Purchase and implement wireless access points for four additional classrooms | June 2017 | $4221.80 | 8133 | Consistent high grad rate |
|  | Purchase and implement 25 new student laptop devices | March 2015 | $7161.60 | 8133 | Consistent high grad rate |

If no School/Center DCP Allocation funding will be spent in this category, please briefly describe below how this category will be addressed by other fund sources.

| Brief description of other activities | Other funding source |
| --- | --- |

Evaluation and Success Criteria for B) Digital Learning and Technology Infrastructure:

Describe the process that will be used for evaluation of the implementation plan and the success criteria for each deliverable.   This evaluation process should enable the district to monitor progress toward the specific goals and targets of each deliverable and make mid-course (i.e. mid-year) corrections in response to new developments and opportunities as they arise.

| Infrastructure Evaluation and Success Criteria |  |  |
| --- | --- | --- |
| Deliverable (from above) | Monitoring and Evaluation and Process(es) | Success Criteria |
|  | Contact Bridget Fetter. | Successful implementation of the system. |

Additionally, if the School/Center intends to use any portion of the DCP allocation for the technology and infrastructure needs area B, s.1011.62 (12) (b), F.S. requires School/Centers to submit a third-party evaluation of the results of the School/Center’s technology inventory and infrastructure needs.  Please describe the process used for the evaluation and submit the evaluation results with the DCP.

C) Professional Development

State recommendations for digital learning professional development include at a minimum, – High Quality Master In-service Plan (MIP) Components that address:

- School leadership “look-fors” on quality digital learning processes in the classroom

- Educator capacity to use available technology

- Instructional lesson planning using digital resources

- Student digital learning practices

These MIP components should include participant implementation agreements that address issues arising in needs analyses and be supported by school level monitoring and feedback processes supporting educator growth related to digital learning.

Please insert links to the School/Center MIP to support this area, attach a draft as an appendix to the School/Center DCP or provide deliverables on how this will be addressed.

Implementation Plan for C) Professional Development:

The plan should include process for scheduling delivery of the School/Center’s MIP components on digital learning and identify other school based processes that will provide on-going support for professional development on digital learning.

| EXAMPLES |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Professional Development Implementation |  |  |  |  |  |
|  | Deliverable | Estimated Completion Date | Estimated Cost | School/ School/Center | Outcome from Section A) |
|  | X# high school teachers participate in professional development aligned with MIP. | May 2015 | $X | Sandy Shores High School | Outcome Example 2 |
|  | X# teachers participate in book study and lesson studies on digital learning | May 2015 | $X | Sandy Shores High School | Outcome Example 2 |

| Professional Development Implementation |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Deliverable | Estimated Completion Date | Estimated Cost | School/ School/Center | Outcome from Section A) |
|  | ISTE | Already met. |  |  |  |
|  | IBIS Best Practices | Already met. |  |  |  |

If no School/Center DCP Allocation funding will be spent in this category, please briefly describe below how this category will be addressed by other fund sources.

| Brief description of other activities | Other funding source |
| --- | --- |

Evaluation and Success Criteria for C) Professional Development:

Describe the process that will be used for evaluation of the implementation plan and the success criteria for each deliverable. This evaluation process should enable the School/Center to monitor progress toward the specific goals and targets of each deliverable and make mid-course (i.e. mid-year) corrections in response to new developments and opportunities as they arise.

| Professional Development Evaluation and Success Criteria |  |  |
| --- | --- | --- |
| Deliverable (from above) | Monitoring and Evaluation and Process(es) | Success Criteria |
|  | Administration | Successfully attended |

D) Digital Tools

Digital Tools should include a comprehensive digital tool system for the improvement of digital learning.  School/Centers will be required to maintain a digital tools system that is intended to support and assist School/Center and school instructional personnel and staff in the management, assessment and monitoring of student learning and performance.

Digital tools may also include purchases and activities to support CAPE digital tools opportunities and courses. A list of currently recommended certificates and credentials can be found at: http://www.fldoe.org/workforce/fcpea/default.asp. Devices that meet or exceed minimum requirements and protocols established by the department may also be included here.

Implementation Plan for D) Digital Tools:

| EXAMPLES |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Digital Tools Implementation |  |  |  |  |  |
|  | Deliverable | Estimated Completion Date | Estimated Cost | School/ School/Center | Outcome from Section A) |
| D.X. | Integrate X sets of instructional materials into the digital tools system | September 2014 | $X | Sunshine Elementary school | Example Outcome 1 |
| D.X. | Offer X additional CAPE digital tool certifications from approved list | 2014-15 | $X | Sandy Shores High School | Example Outcome 2 |

| Digital Tools Implementation |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Deliverable | Estimated Completion Date | Estimated Cost | School/ School/Center | Outcome from Section A) |

If no School/Center DCP Allocation funding will be spent in this category, please briefly describe below how this category will be addressed by other fund sources.

| Brief description of other activities | Other funding source |
| --- | --- |
| Dual enrollment digital textbooks | FEFP |

Evaluation and Success Criteria for D) Digital Tools:

Describe the process that will be used for evaluation of the implementation plan and the success criteria for each deliverable. This evaluation process should enable the School/Center to monitor progress toward the specific goals and targets of each deliverable and make mid-course (i.e. mid-year) corrections in response to new developments and opportunities as they arise.

| Digital Tools Evaluation and Success Criteria |  |  |
| --- | --- | --- |
| Deliverable (from above) | Monitoring and Evaluation and Process(es) | Success Criteria |
|  | Feedback Polk State professors | Reduce drops from successful implementation |
|  |  | Of digital materials. |

E) Online Assessments

Technology infrastructure and devices required for successful implementation of local and statewide assessments should be considered in this section. In your analysis of readiness for computer-based testing, also examine network, bandwidth, and wireless needs that coincide with an increased number of workstations and devices. School/Centers should review current technology specifications for statewide assessments (available at www.FLAssessments.com/TestNav8 and www.FSAssessments.com/) and schedule information distributed from the K-12 Student Assessment bureau when determining potential deliverables.

Implementation Plan for E) Online Assessments:

| EXAMPLES |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Online Assessment Implementation |  |  |  |  |  |
|  | Deliverable | Estimated Completion Date | Estimated Cost | School/ School/Center | Outcome from Section A) |
| E.X. | Implement process for restricting other bandwidth and/or burst bandwidth speeds during testing windows | September 2014 | $X | Sandy Shores High School | Example Outcome 2 |
| E.X. | Purchase 100 additional student devices for assessments | February 2015 | $X | Sandy Shores High School | Example Outcome 2 |

| Online Assessment Implementation |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Deliverable | Estimated Completion Date | Estimated Cost | School/ School/Center | Outcome from Section A) |
|  | Purchase 25 additional devices | 3/15 | $7161.60 | 8133 | Consistent high grad rate |

If no School/Center DCP Allocation funding will be spent in this category, please briefly describe below how this category will be addressed by other fund sources.

| Brief description of other activities | Other funding source |
| --- | --- |
|  | FEFP |

Evaluation and Success Criteria for E) Online Assessments:

Describe the process that will be used for evaluation of the implementation plan and the success criteria for each deliverable. This evaluation process should enable the School/Center to monitor progress toward the specific goals and targets of each deliverable and make mid-course (i.e. mid-year) corrections in response to new developments and opportunities as they arise.

| Online Assessment Evaluation and Success Criteria |  |  |
| --- | --- | --- |
| Deliverable (from above) | Monitoring and Evaluation and Process(es) | Success Criteria |
|  | Evaluation of successful online Test administration. |  |